Program Action Plan (PAP) Update for period Oct – Dec 2022

This note provides a status on the procurement implementation activities undertaken by States/Union Territories (UTs) for the STRIVE Program. This quarterly update captures summary of cumulative data reported by downstream implementing agencies (States, ITIs, and ICs) for period Q3 FY 2022-23 i.e., Oct 2022 – Dec 2022.  One of the key highlights of the report is that the implementing agencies have achieved the stated target of 60% in Year 4, as per Annex 8 of the Project Appraisal Document (PAD) of STRIVE. The achievement of PAP is being measured across PAP 1 and PAP 2. PAP 1 is further categorized into reporting from States and ITIs. The achievement status for period oct 2022 – Dec 2022 is summarized below:

| Measurement Criteria | Number of implementing agencies funded by the project | PAP 1 (Publication of procurement action plan) |  |  | PAP 2 (disclosure and monitoring of procurement related grievances) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target [% and No.] | Status [% and No.] | Remarks | Target | Status | Remarks |
| No. of States (SPIUs and SAMCs) | 33* | 60% (20) | 79% (26) |  | Availability of functional procurement complaint handling and redressal mechanism on project website along with reports generated from the system | The same is available on DGT STRIVE microsite$. No complaint has been received during the period from the IAs that reported the data. | Achieved |
| No. of ITIs | 424^ | 60% (254) | 87% (370) |  |  |  |  |
| No. of ICs | 33# | 60% (20) | 36% (12) |  |  |  |  |
| Total | 490 | 60% (294) | 83% (408) | Achieved |  |  |  |

*Total funded States/UTs are 34. However, no funds have been released to two UTs Chandigarh and Ladakh

^Total number of ITIs funded in the Program is 426, however, two private ITIs of Gujarat have dropped from STRIVE as per SPIU recommendation. Further, only 200 ITIs are earmarked to be directly funded by the World Bank as per DLI matrix where achievement under Q3 i.e. Oct to Dec 2022 is 83%.

#Industry Clusters were not included in the proposed plan of procurement monitoring, however, NPIU has proactively reached out to ICs selected under STRIVE and collected data from 12 ICs

$Link to the redressal mechanism: https://dgt.gov.in/sites/default/files/GuidanceNote-GRM.pdf

Annexure 1: Summary of PAP Compliance data

| S.No. | State/UT | State or UT | WB selected ITIs covered Yes/No | SPIU |  |  | Total no. of ITI's | No. of ITI for which data is reported | ITI-wise PAP compliance |  | Total no. of WB ITI's | No. of WB ITI's for which data is reported | WB ITIs |  | SAMC |  | IC |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Data submitted | PAP-1 | PAP-2 |  |  | PAP-1 | PAP-2 |  |  | PAP-1 | PAP-2 | PAP-1 | PAP-2 | Total | Data reported for ICs | PAP-1 | PAP-2 |
| 1 | Andhra Pradesh | State | Yes | Yes | Yes | Yes | 15 | 15 | Yes | Yes | 8 | 8 | Yes | Yes | No | No | 0 | NA | NA | NA |
| 2 | Andaman and Nicobar Islands | UT | No | No | No | No | 1 | 0 | No | No | 0 | NA | NA | NA | No | No | 0 | NA | NA | NA |
| 3 | Arunachal Pradesh | State | No | Yes | Yes | Yes | 1 | 1 | Yes | Yes | 0 | 0 | NA | NA | No | No | 0 | NA | NA | NA |
| 4 | Assam | State | Yes | Yes | Yes | Yes | 5 | 5 | Yes | Yes | 2 | 2 | Yes | Yes | No | No | 0 | NA | NA | NA |
| 5 | Bihar | State | Yes | Yes | Yes | Yes | 4 | 4 | Yes | Yes | 3 | 3 | Yes | Yes | NA | NA | 0 | NA | NA | NA |
| 6 | Chandigarh | UT | No | Yes | Yes | Yes | 1 | 1 | Yes | Yes | 0 | NA | NA | NA | NA | NA | 0 | NA | NA | NA |
| 7 | Chhattisgarh | State | Yes | Yes | Yes | Yes | 17 | 17 | Yes | Yes | 4 | 4 | Yes | Yes | NA | NA | 0 | NA | NA | NA |
| 8 | Delhi | UT | No | No | No | No | 4 | 0 | No | No | 0 | NA | NA | NA | No | No | 0 | NA | NA | NA |
| 9 | Goa | State | No | Yes | Yes | Yes | 2 | 2 | Yes | Yes | 0 | NA | NA | NA | No | No | 0 | NA | NA | NA |
| 10 | Gujarat | State | Yes | Yes | No | No | 38 | 38 | Yes | Yes | 14 | 14 | Yes | Yes | No | No | 3 | 0 | No | No |
| 11 | Haryana | State | Yes | Yes | No | No | 21 | 21 | Yes | Yes | 16 | 16 | Yes | Yes | No | No | 2 | 2 | Yes | Yes |
| 12 | Himachal Pradesh | State | Yes | Yes | Yes | Yes | 19 | 19 | Yes | Yes | 17 | 17 | Yes | Yes | Yes | Yes | 1 | 0 | No | No |
| 13 | Jammu and Kashmir | UT | No | No | No | No | 7 | 0 | Yes | Yes | 0 | NA | NA | NA | No | No | 1 | 1 | Yes | Yes |
| 14 | Jharkhand | State | No | Yes | Yes | Yes | 3 | 3 | Yes | Yes | 0 | NA | NA | NA | No | No | 0 | NA | NA | NA |
| 15 | Karnataka | State | Yes | Yes | No | No | 22 | 22 | Yes | Yes | 19 | 17 | Yes | Yes | No | No | 4 | 3 | Yes | Yes |
| 16 | Kerala | State | Yes | Yes | Yes | Yes | 19 | 18 | Yes | Yes | 19 | 18 | Yes | Yes | Yes | yes | 4 | 3 | Yes | yes |
| 17 | Madhya Pradesh | State | No | Yes | Yes | Yes | 20 | 20 | Yes | Yes | 0 | NA | NA | NA | No | No | 3 | 0 | No | No |
| 18 | Maharashtra | State | Yes | Yes | Yes | Yes | 76 | 76 | Yes | No | 26 | 26 | Yes | Yes | No | No | 3 | 0 | No | No |
| 19 | Manipur | State | No | Yes | No | No | 1 | 1 | Yes | Yes | 0 | NA | NA | NA | No | No | 0 | NA | NA | NA |
| 20 | Meghalaya | State | Yes | Yes | Yes | Yes | 1 | 0 | No | No | 1 | 0 | NA | NA | No | No | 0 | NA | NA | NA |
| 21 | Mizoram | State | No | Yes | Yes | Yes | 1 | 1 | Yes | No | 0 | NA | NA | NA | Yes | No | 0 | NA | NA | NA |
| 22 | Nagaland | State | No | No | No | No | 1 | 0 | No | No | 0 | NA | NA | NA | No | No | 1 | 0 | No | No |
| 23 | Odisha | State | Yes | Yes | Yes | Yes | 10 | 10 | Yes | Yes | 10 | 10 | Yes | Yes | No | No | 3 | 0 | No | No |
| 24 | Puducherry | UT | No | Yes | Yes | Yes | 2 | 2 | Yes | Yes | 0 | NA | NA | NA | No | No | 0 | NA | NA | NA |
| 25 | Punjab | State | No | No | No | No | 24 | 0 | Yes | Yes | 0 | NA | NA | NA | No | No | 0 | NA | NA | NA |
| 26 | Rajasthan | State | No | No | No | No | 14 | 0 | Yes | Yes | 0 | NA | NA | NA | No | No | 0 | NA | NA | NA |
| 27 | Sikkim | State | No | No | No | No | 1 | 0 | No | No | 0 | NA | NA | NA | No | No | 0 | NA | NA | NA |
| 28 | Tamil Nadu | State | Yes | Yes | Yes | Yes | 16 | 16 | No | No | 14 | 14 | Yes | Yes | No | No | 5 | 0 | No | No |
| 29 | Telangana | State | Yes | Yes | Yes | Yes | 10 | 10 | Yes | Yes | 9 | 9 | Yes | Yes | No | No | 3 | 3 | Yes | Yes |
| 30 | Tripura | State | Yes | Yes | Yes | Yes | 3 | 3 | Yes | Yes | 2 | 2 | Yes | Yes | No | No | 0 | NA | NA | NA |
| 31 | Uttar Pradesh | State | Yes | Yes | Yes | Yes | 29 | 29 | Yes | Yes | 18 | 18 | Yes | Yes | No | No | 0 | NA | NA | NA |
| 32 | Uttarakhand | State | Yes | Yes | Yes | Yes | 8 | 8 | Yes | Yes | 4 | 4 | Yes | Yes | Yes | Yes | 0 | NA | NA | NA |
| 33 | West Bengal | State | Yes | Yes | Yes | Yes | 28 | 28 | Yes | Yes | 14 | 14 | Yes | Yes | Yes | Yes | 0 | NA | NA | NA |
|  | Total |  |  | 26 |  |  | 424 | 370 |  |  | 200 | 196 |  |  |  |  | 33 | 12 |  |  |
| Note: 1. States highlighted in red have not reported data at all. 2. NA donates "Not Applicable" |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Further details of the data reported by States and ITIs can be accessed from the link: Q3 FY 2022-23 Data for the World Bank

PAP1 pertains to disclosure of procurement plans in standard formats by the implementing agencies of the project

PAP 2 pertains to disclosure and monitoring of procurement related grievances/complaints by implementing agencies of the project